ACEHAWK GROUP — UPDATED CRITICAL PATH & 100-DAY PLAN

With Ireland SPV as the Exclusive Funding Gateway

Contents

1. CRITICAL PATH OVERVIEW	2

1. SPV Activation (Day 0–20)	2

2. Intercompany Loan Execution (Day 15–35)	2

3. Demonstrator Acquisition & PMI (Day 30–70)	2

4. BEST Procurement & Engineering (Day 35–100)	3

5. UK OpCo Demonstrator Programme Setup (Day 40–100)	3

6. Governance & Compliance (Day 0–100)	3

2. UPDATED 100-DAY PLAN (WITH SPV AS FUNDING GATEWAY)	4

DAYS 0–20 — SPV ACTIVATION & TREASURY SETUP	4

DAYS 15–35 — INTERCOMPANY LOAN EXECUTION	4

DAYS 30–70 — DEMONSTRATOR ACQUISITION & PMI	5

DAYS 35–100 — BEST PROCUREMENT & ENGINEERING (US OPCO)	5

DAYS 40–100 — UK OPCO DEMONSTRATOR PROGRAMME SETUP	6

3. CRITICAL PATH DEPENDENCIES (VISUAL LOGIC)	7

4. BOARD-READY SUMMARY	7

## 1. CRITICAL PATH OVERVIEW

The critical path now runs through Ireland SPV → US HoldCo → US OpCo / UK OpCo, with all capital deployment, loan execution, and operational readiness dependent on SPV activation.

Below is the updated end-to-end critical path.

CRITICAL PATH (TOP-LEVEL)

### 1. SPV Activation (Day 0–20)

- SPV bank account opening

- KYC/AML completion

- Treasury Policy adoption

- Board resolutions executed

- Capital entry readiness confirmed

Dependency: None
Critical: Yes — all funding flows depend on this.

### 2. Intercompany Loan Execution (Day 15–35)

- Loan A (SPV → US HoldCo) executed

- Loan B (US HoldCo → US OpCo) executed

- Loan C (SPV → UK OpCo) executed

- Loan Register created

- Drawdown templates activated

Dependency: SPV activation
Critical: Yes — procurement and demonstrator ops cannot begin without this.

### 3. Demonstrator Acquisition & PMI (Day 30–70)

- Loan A drawdown

- Escrow funded

- PMI & depot-level acceptance

- FAA conformity

- Insurance binding

- N-Reg documentation

Dependency: Loan A
Critical: Yes — demonstrator programme cannot start without aircraft.

### 4. BEST Procurement & Engineering (Day 35–100)

- Loan B drawdowns

- Pre-buy inspections

- Long-lead procurement

- MRO & depot-level work

- Integration baseline creation

- Engineering documentation

Dependency: Loan B
Critical: Yes — procurement delays impact production and demo readiness.

### 5. UK OpCo Demonstrator Programme Setup (Day 40–100)

- Loan C drawdown

- Poland base setup

- Crew training

- SMS activation

- Ops Manual (N-Reg) adoption

- CAA/EASA declarations

- EU demo schedule finalisation

Dependency: Loan C + demonstrator PMI
Critical: Yes — EU demos cannot begin without regulatory readiness.

### 6. Governance & Compliance (Day 0–100)

- SMS activation

- MOR/Safety reporting setup

- Procurement & engineering compliance

- MEL adoption

- ERP activation

- Monthly treasury reporting

Dependency: Parallel
Critical: Yes — required for audit, investor, and regulator credibility.

## 2. UPDATED 100-DAY PLAN (WITH SPV AS FUNDING GATEWAY)

Below is the full 100-day plan, structured in a board-ready Gantt-style narrative.

### DAYS 0–20 — SPV ACTIVATION & TREASURY SETUP

SPV Setup

- Open SPV bank accounts

- Complete KYC/AML

- Establish treasury controls

- Adopt Treasury Policy

- Approve Delegated Authorities Matrix

Governance

- Board resolutions approving:

  - Treasury Policy

  - Intercompany Loan Agreements

- Establish monthly treasury reporting

Outputs

- SPV is fully operational

- Capital can legally and operationally enter the group

### DAYS 15–35 — INTERCOMPANY LOAN EXECUTION

Loan Agreements

- Finalise and execute:

  - Loan A (SPV → US HoldCo)

  - Loan B (US HoldCo → US OpCo)

  - Loan C (SPV → UK OpCo)

Financial Infrastructure

- Create Intercompany Loan Register

- Activate drawdown templates

- Activate compliance certificates

Outputs

- Funding architecture is live

- Drawdowns can begin

### DAYS 30–70 — DEMONSTRATOR ACQUISITION & PMI

Loan A Drawdown

- SPV funds US HoldCo

- Escrow funded

- PMI scheduled

Technical & Regulatory

- Depot-level PMI

- FAA conformity

- N-Reg documentation

- Insurance binding (SPV as loss payee)

Outputs

- Demonstrator aircraft is airworthy, insured, and ready for EU deployment

### DAYS 35–100 — BEST PROCUREMENT & ENGINEERING (US OPCO)

Loan B Drawdowns

- Pre-buy inspections

- Procurement of long-lead items

- MRO & depot-level work

- Integration baseline creation

- Engineering documentation

- Component tracking activation

Compliance

- Export-control screening

- Procurement logs

- Engineering change control

Outputs

- BEST procurement pipeline activated

- Engineering & MRO operations fully underway

### DAYS 40–100 — UK OPCO DEMONSTRATOR PROGRAMME SETUP

Loan C Drawdown

- Poland base setup

- Crew training

- SMS activation

- Ops Manual (N-Reg) adoption

- CAA Part-NCC declaration

- EASA Part-NCC declaration

- EU demo schedule finalisation

Operational Readiness

- Flight logs

- Maintenance logs

- MOR reporting

- Safety reporting

- Customer demo procedures

Outputs

- UK OpCo fully ready for EU demonstrator operations

## 3. CRITICAL PATH DEPENDENCIES (VISUAL LOGIC)

SPV Activation

↓

Loan Agreements Executed

↓

Loan A → Demonstrator PMI → EU Ops Readiness

↓

Loan B → BEST Procurement → Engineering Baselines

↓

Loan C → UK OpCo Ops Setup → EU Demonstrator Programme

Everything flows from SPV activation.

## 4. BOARD-READY SUMMARY

With Ireland SPV as the sole Funding Gateway, the group now has:

- A clean, regulator-friendly capital entry point

- A defensible intercompany lending architecture

- A sequenced 100-day plan aligned to procurement, engineering, and demonstrator operations

- A clear critical path that investors and auditors can follow

- A governance framework that supports future scaling